## RAID LOG
| RAID Log | Should you face any difficulty in completing the RAID Log, please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f | [8 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 3 | 0 | 0 | 0 | 0 | 0 | Instruction to use the RAID log template: • All fields must be duly filled • The descriptions for what to be filled in each of the fields are provided in the template. • Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes. • Understand what risks, assumptions, issues, and dependencies are from the description provided in the methodology document • Select the category of RAID from the dropdown menu provided in the “RAID category” field in the template. • Provide a valid description of the RAID category that you have selected in the “description” field provided. • Describe the impact the RAID category you have selected will have on the project in the “impact field”. • Describe how the impact of the selected RAID category can be reduced on the project in the “mitigation field” in the template. • Mention the responsible person for working on the selected RAID category in the “owner” field in the template. • Select the priority with which the selected RAID category needs to be mitigated. The following levels of priority are given in the drop-down menu. Select; o Negligible: if the RAID category is not going to make an impact on the project o Low: if the raid category is going to make very small impacts on the project o Moderate: if the RAID category is going to make a few impacts which can affect the project adversely. o High: if the RAID category is going to make major impacts on the project adversely. o Critical: if the raid category is going to affect the project at any stage. • Provide risk priority number based on the priority selected for the RAID category selected. • Select the status of the RAID category selected. Two options are provided in the drop-down menu. Select; o Open: if the responsible person is still working on the RAID category selected. o Closed: if the responsible person has worked on the RAID category and is solved.
| Project title: | Students Analysis for gaining insights |  | Project Id: |  | Project Manager: | Harshada Topale |  |  | Assumption | 2 | 0 | 0 | 0 | 0 | 0
[10 empty] | Issue | 2 | 0 | 0 | 0 | 0 | 0
| DOCUMENT VERSION: | 1 |  | Last Updated date: | 2023-09-27 | Project Team Lead: | SHRAVANI SHETE |  |  | Dependency | 2 | 0 | 0 | 0 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 9 |  |  |  |  | 0
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Inability to do required maintenance on time. | Impact on the project schedule and cost. | Have a dedicated maintenance team for the project .The project budget should be considered. | Project Manager | High | RPN (S x L x D): 6 x 2 x 5= 60 | Closed | Risk
2 | Risk | Long supply delivery time | Impact on project schedule | Search for vendors who will deliver the resources on timeand within the proposed budget. | Project Manager | Critical | RPN (S x L x D): 6 x 4 x 4 = 96 | Closed | Assumption
3 | Risk | Data Quality. | Inaccurate data in the dataset, which may affect the analysis. | Perform thorough data validation and cleaning before analysis. | Project Manager | High | RPN (S x L x D): 7 x 5 x 5 = 175 | Closed | Issue
4 | Issue | Missing Values | Some columns in the dataset may have missing values that need to be addressed during analysis. | Perform elimination of missing values using preprocessing | Project Manager | Moderate |  | Closed | Dependency
5 | Issue | Data Transformation | Converting non-numeric columns (e.g., income ranges) to numeric values may pose challenges. | Normalizing the data | Project Manager | Moderate |  | Closed
6 | Dependency | Python Libraries | The analysis depends on specific Python libraries that need to be installed and up-to-date. | Updating tfhe libraries from time to Time | Project Manager | Critical |  | Closed | Open
7 | Dependency | Data Source | The project depends on the availability and access to the student dataset. | Dataset should be available throughout | Project Manager | High |  | Closed | Closed
8 | Assumption | Data Availability | Available data is sufficient to make an analysis | Verify data availability and access permissions before starting the project. Establish communication with data owners or providers to address any data availability issues. | Project Manager | Moderate |  | Closed
9 | Assumption | Data Consistency | Consistent data dtermines the quality of the analysis | Develop data consistency checks and validation procedures. Document data schema and format to ensure data consistency. | Project Manager | Moderate |  | Closed | Critical
10 | [8 empty] | High
11 | [8 empty] | Moderate
12 | [8 empty] | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24